## Features
Project: Shopbee
Group: 08
ID | Feature Name | Description | Remark
UC01 | Login | User accesses their account on the online shopping platform.
UC02 | Manage User Account | Actions taken by an admin to manage user accounts on the online shopping platform.
UC03 | Browse Products | User explores and views products on the online shopping platform.
UC04 | View Product Details | Provides a detailed overview of a chosen item in online shopping.
UC05 | Manage Products | The actions taken by an admin to add, update, or remove products from the online shopping platform.

## Test Cases
Function/Feature ID | Case ID | Test case name | Test step | Expected Result (ER) | Actual Result | Status | Tester | Tested Date | Remark
Function 01: Login
UC01 | UI01 | Log in with correct Username and Password | 1. Enter User Name: "abcd " 2.Enter Password: "abcd" 3. Click "Ok" button | 1. Authenticated 2. A welcome message will be displayed |  |  | NAThu | 2024-02-01
UC01 | UI02 | Log in with incorrect Username | 1. Enter User Name: "abcx" 2. Enter Password: "abcx" 3. Click "Ok" button | 1. Unauthenticated 2. A wrong user-account notice will be displayed |  |  | NAThu | 2024-02-01
UC01 | UI03 | Login with blank User name and Password | 1. Enter User Name: " " 2. Enter Password: " " 3. Click "Ok" button | 1. Disallows the user to proceed 2. The error message should be displayed |  |  | NAThu | 2024-02-01
UC01 | UI04 | Login with Special characters of Username and blank Password | 1. Enter User Name: " " 2. Enter Password: "'or'$'='$' " 3. Click "Ok" button | 1. Disallows the user to proceed 2. The error message should be displayed |  |  | NAThu | 2024-02-01
UC01 | UI05 | Login with Special characters of User name and Password | 1. Enter User Name: " 'or'$'='$' " 2. Enter Password: " 'or'$'='$' " . Click "Ok" button | 1. Disallows the user to proceed 2. The error message should be displayed |  |  | NAThu | 2024-02-01
Function 02: Manage User Account
UC02 | UI01 | Admin deletes an available account | 1. Access the account which is necessary to delete 2. Click "Delete" button | 1. A "Are you sure to delete this account?" message is displayed 2.1. If click "Yes" button -> A successful message is displayed 2.2. If click "No" button -> Message disappears and nothing changes. |  |  | NDVLinh | 2024-02-01
UC02 | UI02 | Admin adds an account which enters full information | 1. Click "Add new account" button 2. Enter that account's information 3. Click "Ok" button. | 1. A successful message should be displayed |  |  | NDVLinh | 2024-02-01
UC02 | UI03 | Admin adds an account which enters missing information | 1. Click "Add new account" button 2. Enter that account's information 3. Click "Ok" button. | 1. A successful message should be displayed |  |  | NDVLinh | 2024-02-01
UC02 | UI04 | Admin edits an available account | 1. Access the account which is necessary to edit 2. Click "Edit" button | 1. A "Are you sure to edit this account?" message is displayed 2.1. If click "Yes" button -> A successful message is displayed 2.2. If click "No" button -> Message disappears and nothing changes. |  |  | NDVLinh | 2024-02-01
UC02 | UI05 | Admin edits an available account but it enters missing information | 1. Access the account which is necessary to edit. 2. Click "Edit" button. 3. Edit the necessary information. 4. Click "Ok" button. | 1. A "Are you sure to edit this account?" message is displayed 2.1. If click "Yes" button -> A successful message is displayed 2.2. If click "No" button -> Message disappears and nothing changes. |  |  | NDVLinh | 2024-02-01
Function 03: Browse Products
UC03 | UI01 | Click the product | 1. Click the product | 1. The page of detailed product is displayed |  |  | NAThu | 2024-02-01
UC03 | UI02 | Turn to another page | 1. Click |  |  |  | NAThu | 2024-02-01
UC03 | UI03 | Search the product's name |  |  |  |  | NAThu | 2024-02-01
UC03 | UI04 | Search the product's name without enter anything |  |  |  |  | NAThu | 2024-02-01
UC03 | UI05 | Click a product's category |  |  |  |  | NAThu | 2024-02-01
Function 04: Register
UC04 | UI01 | Click "Register" button |  |  |  |  | NAThu | 2024-02-01
UC04 | UI02 | Enter full information |  |  |  |  | NAThu | 2024-02-01
UC04 | UI03 | Not enter anything and Click "Register" button |  |  |  |  | NDVLinh | 2024-02-01
UC04 | UI04 | Only enter necessary field |  |  |  |  | NDVLinh | 2024-02-01
UC04 | UI05 | Enter lack of one of necessary fields |  |  |  |  | NDVLinh | 2024-02-01
Function 05: Manage Products
UC05 | UI01 | Admin deletes an available product |  |  |  |  | NAThu | 2024-02-01
UC05 | UI02 | Admin adds a new product |  |  |  |  | NAThu | 2024-02-01
UC05 | UI03 | Admin edits an available product |  |  |  |  | NAThu | 2024-02-01
UC05 | UI04 | Admin change the picture of a product |  |  |  |  | NAThu | 2024-02-01
UC05 | UI05 | Admin update information a product |  |  |  |  | NDVLinh | 2024-02-01